## Task List
WhatsApp V2 — Task List (15 Tasks)
Sr. No | Phase | Task Detail | Status | Start date | End Date
Phase 1: Basic Setup (Project, Servers & Monitoring)
1 | 1 | Project Setup – create one code folder for all apps, fix the message formats everyone will use, and make the full system run on a laptop with Docker. Add auto code checks on every change. | Not Started | 17 July 26 | 18 July 26
2 | 1 | Server Setup – create the Kubernetes cluster in the cloud, add HTTPS security, and set up auto-deploy so new code goes live safely with a small test rollout first. | Not Started | 19 July 26 | 20 July 26
3 | 1 | Database & Monitoring Setup – install the main database (PostgreSQL), cache (Valkey), message queue (NATS) and file storage (MinIO). Add daily backups and dashboards to watch system health. | Not Started | 21 July 26 | 22 July 26
Phase 2: Login & Message Security
4 | 2 | User Login & Devices – sign up with phone number and OTP, keep users logged in safely with tokens, add a 2FA PIN, and let users see and remove their logged-in devices. | Not Started | 23 July 26 | 25 July 26
5 | 2 | End-to-End Encryption – add the Signal encryption library so only sender and receiver can read messages. The server can never read chats. Add QR code to verify contacts. | Not Started | 26 July 26 | 28 July 26
Phase 3: Core Chat Features
6 | 3 | Live Connection Gateway – build the server that keeps every phone connected in real time. If the connection drops, the app reconnects and no message is ever lost. | Not Started | 29 July 26 | 31 July 26
7 | 3 | 1-to-1 Chat – send and receive messages with sent / delivered / read ticks. Offline users get messages when back online. Also add edit, delete, reactions, typing and online status. | Not Started | 1 August 26 | 3 August 26
8 | 3 | Push Notifications – show new message alerts on locked phones (Android and iPhone) without ever sending readable text through Google or Apple servers. | Not Started | 4 August 26 | 5 August 26
Phase 4: Groups, Media & Mobile App
9 | 4 | Group Chat – groups up to 1,024 members with admins, permissions, invite links, @mentions and group receipts. Removed members can no longer read new messages. | Not Started | 6 August 26 | 8 August 26
10 | 4 | Photos, Videos & Files – send media up to 25 MB. Files are encrypted, upload in parts, and resume if the network drops. Show small blurred previews while loading. | Not Started | 9 August 26 | 11 August 26
11 | 4 | Mobile & Web App (Offline First) – build the phone app and web app. Chats are stored on the device, work fully offline, sync when back online, with fast search and dark/light themes. | Not Started | 12 August 26 | 16 August 26
Phase 5: Calls, Extras & Launch
12 | 5 | Voice & Video Calls – 1-to-1 and group calls up to 32 people with screen share and background blur. Calls are encrypted and ring on locked phones. Call connects in under 3 seconds. | Not Started | 17 August 26 | 21 August 26
13 | 5 | Push-to-Talk (Walkie-Talkie) – press and hold to speak in a room. Only one person can talk at a time, others wait in a queue. Voice starts in under 200 ms. | Not Started | 22 August 26 | 24 August 26
14 | 5 | Multi-Device, Stories & Backups – link extra devices by QR code with full chat history, add 24-hour stories with view counts, and encrypted chat backups only the user can open. | Not Started | 25 August 26 | 27 August 26
15 | 5 | Testing, Security Check & Launch – load test with 20,000 users at once, outside security audit, disaster-recovery drills, fix all critical issues, then go live. | Not Started | 28 August 26 | 30 August 26