## Task Plan
WhatsApp V2 — Project Task Plan
Derived from HLD.md v1.0 (2026-07-14) · 15 execution tasks in dependency order · Scope: 20k concurrent users · Phases P0–P4 map to HLD §23 roadmap
# | Phase | Title | Description | Definition of Done (Exit Criteria) | Depends On | Est. Duration | HLD Ref | Status
1 | P0 | Monorepo, Contracts & Dev Environment | Set up the monorepo per HLD Appendix A (clients/, server/, deploy/, ops/, docs/). Configure the Go workspace, React + React Native scaffolds, and the protobuf toolchain (buf) as the single source of truth for WS frames, REST/gRPC and NATS event contracts. Build the Docker Compose dev stack (PostgreSQL, Valkey, NATS, MinIO) so the full system runs on a laptop. Wire CI PR gates: lint, unit tests, SAST (semgrep/gosec), protobuf breaking-change check. | docker compose up boots the full data layer + skeleton services; CI runs green on a sample PR. | — | 1 week | App. A, §19 | Not Started
2 | P0 | Infrastructure & GitOps (K8s + ArgoCD) | Provision the Kubernetes cluster with Terraform using the node pools from §17.1 (general, rtc, data) plus the observability node. Install Envoy Gateway (TLS 1.3), cert-manager, external-dns, ArgoCD (app-of-apps) and Argo Rollouts for canary deploys. Create dev / staging / prod overlays that reuse identical Helm charts. | A Git push deploys a sample app to staging via ArgoCD canary; HTTPS ingress with valid certificates is live. | 1 | 1–2 weeks | §17, §19 | Not Started
3 | P0 | Data Layer & Observability Stack | Deploy PostgreSQL 17 (CloudNativePG, primary + replica, PgBouncer), Valkey with Sentinel, 3-node NATS JetStream, and 4-node MinIO (EC 2+2). Configure WAL-G continuous archiving to the off-site bucket (RPO ≤ 5 min). Stand up Prometheus, Grafana, Loki and Tempo with OpenTelemetry wiring and the §18 SLO alert rules. | PostgreSQL failover kill-test passes; a PITR restore is performed and documented; golden-signal dashboards render. | 2 | 1–2 weeks | §7, §17.4, §18 | Not Started
4 | P0 | Auth, Identity & Device Management | Implement phone-OTP registration behind a pluggable SMS-provider interface with the §15.4 rate limits and a spend circuit-breaker; optional email fallback. Issue short-lived access JWTs (10 min) with rotating refresh tokens and reuse detection; add the Argon2id-hashed 2FA registration PIN. Build the device registry (1 primary + ≤ 4 linked), session listing and atomic revocation. | Register / login / refresh / revoke flows pass integration tests, including OTP abuse-limit and token-reuse cases. | 3 | 2 weeks | §15.2, §7.1 | Not Started
5 | P0 | E2EE Key Infrastructure (libsignal) | Integrate libsignal in the clients and build server endpoints for publishing / fetching public prekey bundles (identity key, signed prekey, one-time prekeys). Implement X3DH session establishment and Double Ratchet messaging for pairwise chats, safety-number / QR verification with key-change warnings, and hardware-backed key storage on device. | Two test clients establish a session and exchange messages the server demonstrably cannot decrypt; key-change warning fires on re-registration. | 4 | 2 weeks | §15.1, §7.1 | Not Started
6 | P0 | WebSocket Gateway | Build the stateless Go ws-gateway: WSS with protobuf frames, JWT handshake, route:{device} registry in Valkey, one NATS subject subscription per connected device, jittered 30 s heartbeats. Implement the session-resume protocol (resume token + inbox cursor) and SIGTERM connection draining with jittered reconnect hints. | 20k simulated connections held on one pod; a rolling restart of all gateway pods loses zero server-ACKed messages (chaos test). | 3, 4 | 2 weeks | §8.1, §17.2 | Not Started
7 | P0 | 1:1 Messaging Core (Relay Model) | Implement the chat context: UUIDv7 idempotent sends with Valkey dedupe, per-conversation sequences, ciphertext inbox rows (30-day TTL, partitioned) deleted on device ACK, live fan-out over NATS. Deliver the full state machine sending → sent → delivered → read with batched receipts, overlay events (edit ≤ 15 min, delete-for-everyone ≤ 48 h, reactions, pins), and typing + presence using the §8.5 subscription model. | Offline recipient receives messages on reconnect; receipts flow end-to-end; p95 online↔online latency ≤ 500 ms under load. | 5, 6 | 2–3 weeks | §8, §7.2 | Not Started
8 | P0 | Push Notifications | Build notification-svc consuming the NATS dispatch stream: data-only FCM / APNs pushes (never plaintext), token registry with provider-feedback invalidation, retry / backoff isolation so provider outages never back-pressure chat. Client side: iOS Notification Service Extension and Android fetch-decrypt-render; groundwork for VoIP push (PushKit / high-priority FCM). | Locked devices show decrypted message notifications; a simulated FCM outage leaves messaging latency unaffected. | 7 | 1–2 weeks | §13 | Not Started
9 | P1 | Group Chat (Sender Keys) | Implement groups up to 1,024 members: CRUD, multi-admin roles and permissions bitmap, announcements mode, invite links + QR with revocation, @mentions. Encrypt once with Sender Keys and fan out ciphertext asynchronously off the ACK path; rotate keys on membership change; enforce per-sender big-group rate limits; aggregate delivered / read receipts with per-member detail. | 1,024-member group passes the fan-out load test; a removed member provably cannot decrypt subsequent messages. | 7 | 2–3 weeks | §8.3, §5 | Not Started
10 | P1 | Media Pipeline | Build media-svc: file-type allowlist, 25 MB cap, per-user quotas, S3 multipart presigned URLs, refcount / TTL garbage collection. Client side: compression (WebP / AVIF images, H.264 ≤ 720p video, Opus voice), AES-256-GCM per-file encryption, thumbnail + blurhash inside the E2EE envelope, parallel resumable chunk uploads direct to MinIO, multi-file sends with progress indicators. | A 25 MB upload interrupted mid-transfer resumes with only the missing parts; recipient downloads, verifies hash and decrypts. | 7 | 2 weeks | §9 | Not Started
11 | P1 | Client Apps — Local-First UX | Build out the React Native (Expo) and React + Vite PWA clients: SQLCipher store (chats, messages + FTS5, attachments, outbox, sessions), optimistic UI with outbox retries, delta sync cursors, client-side message / media search, chat-list virtualization, lazy media with blurhash placeholders, dark / light themes, responsive phone / tablet / desktop layouts, full offline mode. | Complete chat UX works offline and syncs cleanly on reconnect; local search returns results in under 100 ms. | 7, 10 | 3–4 weeks | §4.1, §7.3, §14, App. C | Not Started
12 | P2 | Voice & Video Calling | Deploy the LiveKit pool + coturn on the rtc nodes. Implement call-ctl: room lifecycle, short-lived join JWTs, ring state machine (45 s → missed), metadata-only call records. Ship 1:1 and ≤ 32-party group calls with simulcast + active speaker, screen share, on-device background blur, E2EE frame encryption keyed from Signal sessions, ICE restart under 5 s, CallKit / ConnectionService lock-screen ringing, and Opus DTX + FEC low-bandwidth mode. | p95 call setup ≤ 3 s; locked-phone ringing works on both platforms; a 32-party call stays stable at 5% simulated packet loss. | 8, 11 | 3–4 weeks | §10 | Not Started
13 | P3 | Push-to-Talk (PTT) | Build PTT on audio-only LiveKit rooms where every participant keeps a pre-negotiated, server-muted mic track. Implement the Valkey floor token with fencing sequence, FIFO request queue with position feedback, 500 ms speaker heartbeats (2 missed → auto-release), 60 s max-speak limit, and server-side publish-permission enforcement so no client can transmit without the floor; show the active speaker and queue in the UI. | p95 press-to-audio ≤ 200 ms with 200 listeners; zombie-speaker fencing chaos test passes. | 12 | 2 weeks | §11 | Not Started
14 | P3 | Multi-Device, Stories & Encrypted Backups | Implement QR device linking with a primary-signed device list and history bootstrap via encrypted device-to-device transfer. Ship stories: per-story key distributed to the audience snapshot, 24 h TTL hard delete, view receipts and reactions. Add client-encrypted backups (Argon2id passphrase or 64-digit recovery key) to MinIO, with explicit key-loss warnings in the UX. | A newly linked device receives full history; stories vanish everywhere at 24 h; a backup restores on a factory-reset device. | 9, 10, 11 | 2–3 weeks | §7.2–7.3, §12 | Not Started
15 | P4 | Hardening, Load Test & Launch | Run the 20k-concurrent load test with 3× burst and continuous synthetic probes. Commission an external security audit + penetration test and close all criticals. Execute DR game days (PITR restore, region loss, RTO ≤ 60 min), tune alerts to the §18 SLOs, finalize runbooks and canary gates, implement GDPR export / delete, and complete the go-live checklist. | All SLOs green for 2 consecutive weeks under synthetic load; audit criticals closed; production launch. | All | 3–4 weeks | §16–§23 | Not Started